## Sheet1
Milestone |  |  |  |  | 2017-2018
[5 empty] | Octorber |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July
[5 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
No. | Activity |  |  | Who
1 | Foundation of Data Science
Coursework 3
|  | Choose Topic | 2017-10-27 | bar: Octorber W3
Design Project | bar: Octorber W4 to November W5
|  | Prepare pitch | 2017-11-01 | bar: Octorber W4
Data Collection | bar: November W5 to November W6
Data Cleaning | bar: November W6 to November W7
Develop Machine Learning Model | bar: November W8 to December W11
Data Visualisation | bar: November W8 to December W11
Testing | bar: December W11
Write Report and Prepare for presentation | bar: December W10 to December W11; January W15
Foundation of Data Science - CR3
Topic
Pitch
Present& report
Feedback
Should be done
Note on C16: Auu: Design Workflow Choose Technology Draft UI